## Sheet1
Pre-production timeline
week |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
hardware install | bar: Pre-production timeline 0 to Pre-production timeline 1
define expectation | bar: Pre-production timeline 0 to Pre-production timeline 2
Exp BGRS tour | bar: Pre-production timeline 3 to Pre-production timeline 4
Mop creative | bar: Pre-production timeline 5 to Pre-production timeline 12
sketch design | bar: Pre-production timeline 5
intro tech restrictions | bar: Pre-production timeline 5
gameplay | bar: Pre-production timeline 5 to Pre-production timeline 9
environments | bar: Pre-production timeline 6 to Pre-production timeline 7
storyline | bar: Pre-production timeline 5 to Pre-production timeline 8
concept art | bar: Pre-production timeline 6 to Pre-production timeline 12
dev | bar: Pre-production timeline 6 to Pre-production timeline 12
interactions | bar: Pre-production timeline 6 to Pre-production timeline 10
asset integration | bar: Pre-production timeline 8 to Pre-production timeline 11
testing | bar: Pre-production timeline 10 to Pre-production timeline 12